## Project schedule
| AI Data Extractor |  |  |  |  | Project start: | [7 empty] | 2025-06-09
[6 empty] | Display week: | [7 empty] | 1
[6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01
| TASK | ASSIGNED TO | START | END | time axis 2025-06-09 to 2025-09-07
 | time axis 2025-06-09 to 2025-09-07
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Stakeholder Identification | Project Manager | 2025-06-09 | 2025-06-11 | 3
| Develop charter | Project Manager | 2025-06-09 | 2025-06-12 | 4
| Initial Announcement | HAIL Leadership | 2025-06-12 | 2025-06-13 | 2
| Establish Comms | Project Manager | 2025-06-11 | 2025-06-13 | 3
Planning and design
| Develop Communication Plan | Communications Team | 2025-06-16 | 2025-06-20 | 5
| Develop Training Program | HR and Training Team | 2025-06-20 | 2025-07-04 | 15
Execution
| Conduct Training sessions | HR and Training Team | 2025-07-07 | 2025-07-18 | 12
| Pilot Phase Implementation | IT Team | 2025-07-14 | 2025-08-01 | 19
Evaluation
| Monitor Pilot Phase | IT Team | 2025-08-04 | 2025-08-16 | 13
| Collect Feedback | Project Manager | 2025-08-16 | 2025-08-20 | 5
Full Rollout
| Full Implementation | IT Team | 2025-08-21 | 2025-09-06
| Continuous Monitoring | IT Team | 2025-09-06 | Ongoing